## Issue List
Issue Number | Issue | Priority 1 to 5 | Issue type Bug/change/feature | Screenshot no | Expected results | Existing Result | Solution | Resolved Yes/No | Resolved by | Resolved on | Developer Comments | Review comments
1 | desk booking |  | bug |  |  | while booking desk, if i enter time which has already been booked, its getting into the layout page and not going back |  | YES
2 | room booking |  | feature |  |  | soon after booking the room, the " click here to book parking" option is not working | Removed as TimeBeing | YES
3 | room booking |  | feature |  |  | while booking room, check whether next button is working or not on second section |  | YES
4 | room booking |  | feature |  |  | and sometimes even the book button on last section wont works | I add Color to button and if Color change to Adappt Green so validation checked or else it will transparent | YES
5 | room booking |  | feature |  |  | the next button on second section works only if i select repeat booking | Issue is fixed on latest release v1.0.3 | YES | Dhamodar
6 | room,desk,parking |  | change |  |  | the errors while booking are displaying on the background which is not vissible(i.e the dashboard which will be on backsreen) | on Which part booking that error thoast display behind bottom page ? | NO
7 | timezone |  | bug |  |  | and the time slots will be in 24hr format and somewhere it will be 12hr format | Resolved | YES |  |  | in which part of screen we get this issue
8 | profile page |  | change |  |  | Logout should be written with button to log out | Icon will be Self explainmetry | YES
9 | profile page |  | change |  |  | Show an indication that we can change profile photo
10 | parking slot booking |  | bug |  |  | Parking chart is not taking a booking |  | YES
11 | room,desk,parking |  | change |  |  | Enable selecting date and time by pressing date and time also, not just “date” and “time” | Solved | YES
12 | Touch is not fast, slow appearances |  | feature |  |  | Touch is not fast, slow appearances | Solved | YES
13 | dashboard |  | feature |  |  | notification bell doesnt show anything | Removed | YES
14 | room,desk,parking | 5 | bug |  |  | Sign in, Cancel, Done, incomplete spelling | Only OnePlus mobile as this issue | NO
15
16 | room booking |  | bug |  |  | room booking - drop down on location is misplaced | Solved | YES
17 | room,desk,parking |  | feature |  |  | we wont get any errors if we wouldn't select any options like date, time, amenities
18 | room booking |  | bug |  |  | rooms are getting booked without informing invitees | Solved | YES
19 | login page |  | change |  |  | and also change the font of username and the format of Sign in | Solved | YES
20 | room,desk,parking |  | feature |  |  | better to add the loader wherever required, otherwise it looks like mobile got hung
21 | calender |  | feature |  |  | calender works very slow and we cannot go through the future dates and schedules | Solved | YES
22 | room booking |  | change |  |  | and the purpose of meeting responses only if we enter more than 4 characters | Obivosily as Minimum Caracter word required to validate | YES
23 | room booking |  | bug |  |  | will get an error if we try to book again on the same timings that we have already booked, the next button wont work after updating the time slot | API Issue
24 | room booking |  | bug |  |  | I couldn't book a room, if I try to book once after getting an error message
25 | room booking |  | feature |  |  | while updating booked room, purpose is not working correctly and also we cannot opt for repeat booking
26 | profile page |  | feature |  |  | the pofile photo can be easily uploaded but its not consistent ie it gets dissappear within a minute
27 | desk booking |  | feature |  |  | not getting the updated mail notification once after changing the timings of booked desk (Updated Not coming)
28 | desk booking |  | featute |  |  | here Im not getting an error if I book a two different seats at same particular period of time
29 | room booking |  | change |  |  | no need to display room name and location twice
30 | parking slot booking |  | bug |  |  | not getting the booking confirmation mail

## Sheet4
| Test Cases | expected result | existing result
Login page | Enter credentials: username password | Login should happen if user is registered | while logging in, if we enter userId, getting an error lke error cant login
Login shouldn't happen if user is registered
| forgot pasword | if user has forgot the password, then will get an otp fo his respective mail id
dashboard | display the list of booked seats, rooms, and parking slots | should display the list of booked seats, rooms, and parking slots along with the duration, date, and time | after refreshing the page, there will be duplication in the list and also it displays the negative value in the booking duration
Room booking
| select location | location should get selected | here we can select "click here to select location" as an option that means it also getting selected if we select that and no need to display the location name twice
| select room | room should get selected and throws an error if two rooms get selected | same error as location
| select room size | room size should get selected and throws an error if two rooms get selected at a time | room size get selected, if we select two room sizes, it will throw an error and meanwhile the selected room size gets dissappear
| select amenities | amenities should get selected, can select 'n' number of amenities
| select time and date | required date and time get selected and should throw an error if we select the passed time and date | *Both calender and time clock are taking much time to get load *There is no error if i select the passed time and date *And there is an inconsistancy in the time format *And not able to select the time minute-wise
| select repeat mode | required room can be selected and also we can select the days to repeat meeting schedule
| select end date | required date can be selected to end the repeat mode
| select non-repeat mode | required room can be selected for a single day without any repetation | the page gets load to the next page only if we select the repeat mode
| enter purpose | gives purpose of the meeting, if not throw an error | its not throwing error and also its not getting booked, if we wouldn't have given the purpose
| select invitees | can invite set of members for the meeting, they should get a notification mail about the meeting. And also they shuld get a updated mail if any changes made in the schedule, also shouldn't get booked if members wouldnt have been informed | room getting booked though we wouldnt invite any staff members for the meeting
Desk booking

## ScreenShots lists
ScreenShots with No