## browsestack issues
Mobile Models
Samsung s8 | 1 | not displaying booked schedules on the dashboard
| 2 | dashboard is displaying only past events on the dashboard
| 3 | if i scroll down the calender, the whole view gets disturbed and the page doesnt get refreshed.
Samsung A10 | 1 | the layout view is not movable while booking seat or parking slot as well as room booking
2
vivo
one+ 7

## new issues(jan 14)
Issue Number | Issue | Priority 1 to 5 | mobile version | Issue type Bug/change/feature | Screenshot no | Expected results | Existing Result | Solution | Resolved Yes/No | Resolved by | Resolved on | Developer Comments | Review comments
1 | desk,seat,calender view |  |  | feature |  | time selector should be same in all the booking modules | change the time picker/time selector of seat and parking slot same as layout view
2 |  |  |  | change |  |  | grey out the start-time while selecting the end-time
3 | room booking |  |  | feature |  |  | we can select only one amenity while booking
4 | room booking |  |  | feature |  |  | Couldn't edit amenities while updating
5 |  |  |  | feature |  |  | Couldn't edit the to-date alone while editing the event
6 |  |  |  | change |  |  | No need of date on the card displayed on the dashboard, anyhow it shows the current day details
7 |  |  |  | change |  |  | once after layout booking confirmation, t get back to the layout view again , not to the home page
9 |  |  |  | feature |  |  | taking negative timings
10 | [6 empty] | time slot issue (once after selecting startin time, the time scroll not getting refreshed)
11 | [6 empty] | next button wont appear on the first page (when changing the time, once aftr getting an error if we haveanother meeting at that time)
12 | [6 empty] | calender icon, layout view timings,
13 | [6 empty] | user can select the finished or previous month dates while selecting the repeat mode
2021-02-03
1.give next button on the first page while editing the room | [6 empty] | done
2.email has been send to you should comes in the next line | [6 empty] | done
3.if i try to book for the future date, in the confirmation page(page 3), it display the current date as an end-date | [6 empty] | done
4.the calender keeps loading forever,and the scedules keeps changing, and dates keeps shifting, once after scrolling the below displayed scedules | [6 empty] | done
5.Ive booked a room on 5th feb, but the calender is not displaying it, if I select date-5 explicitly also, it just keeps loading forever | [6 empty] | not resolved(its displying no meeting on this day) | Issue not found | YES | dhamodar | 2021-05-02 | it fixed please cross check
6. i think its better if we display the meeting title on the card that are displayed on the dashboard, just to avoid confusions | [6 empty] | not done | we do add this in next version as we working on white labeling our app so we can't share in-complete version as of now after adding complete feature of white label on that version we do add this feature too
7.the layout view doesnt get refreshed, once after booking done | [6 empty] | done
8.komstadt has asked to remove the unused/irrelevent invitees/attendees. yet not removed. | [6 empty] | not done | please approach team-mates or venu alter those usernames
9.while updating the booked room, it is possible to select previous month in the repeat mode | [6 empty] | not done(it doesnt give any error, instead it takes current date as recurring till date) | Issue not found | YES
10.still the time issue mentioned regarding layout view is present, it could be possible to book a room with same start-time and end-time | [6 empty] | not resolved(its displaying same start-time and end-time with 0min duration) | i think tester choose wrong version
11. once after selecting future date while booking room on layout view, the very next time the date will be in the future date only bydefault(not getting refreshed) | [6 empty] | done
12.komstadt has asked to remove unecessary questionings(like once after selecting the room in the layout view/ while logging out). Gagandeep has to confirm that | [7 empty] | Please discuss wtih gagandeep about this
| For issue 12, remove questions when selecting the room and desk on layout view, but keep the Log Out question | [5 empty] | not done | Please discuss wtih gagandeep about this
2021-02-05
1.yesterday i've booked a room for today, its displaying on the demo site dashboard, but not on the mobile app dashboard | [6 empty] | done | solved please cross check
3. while booking seat/parking slot, if i dont select end-time also its getting booked by taking end-time as 11:59 | [6 empty] | done
4. when user wanted to edit the schedule in the calender, please redirect the user to the editing-page when clicked on it | [6 empty] | future
1.choose the different picker i.e simple during the time selection
2.font of Saturday should change, suggested by komstadt
3. meeting title should highlight