## Sheet1
Issue Number | Issue | Priority 1 to 5 | mobile version | Issue type Bug/change/feature | Screenshot no | Expected results | Existing Result | Solution | Resolved Yes/No | Resolved by | Resolved on | Developer Comments | Review comments
1 | desk booking | 1 |  | feature |  | should get a booking confirmation mail and also an updated mail notification | not getting an updated mail notification once after changing the timings of booked desk (Updated Not coming) | Feature is not there in web app also so need implement and Venu should respond to this | YES |  |  |  |  | Desk And Parking Booking: 1) end time should be greater than start time, before going to select a seat/parking slot. (Fixed) 2) No need of toDate for desk / parking slot booking.(Fixed) 3) After selecting a seat, it is better to show confirmation prompt instead of directly booking a seat / parking slot (Fixed). Dashboard: 1) Better if legends are shown which represents ongoing, next and previous meetings.(Fixed) 2) Sorting meetings based on time need to be implement.(future Implement) 3) In header the logo for profile need to be changed and if possible move adappt logo to left.(feature) 4) Not able see previous month, week meetings in calendar view.(Possible to see and need to fine tune...! ) 5) After booking a seat/ room/ parking slot need to update the dashboard automatically.(feature) Profile Page: 1) The update button is not fully visible, it is overlapping.(Discuss) Room Booking: 1) While filtering the rooms based on location and rooms not working sometimes, Need to show error message if no rooms are available.(Fixed) 2) Show error message if user tries to book to without selecting any rooms .(fixed) 3) Attendee list scrolling is not visible properly, need to change some styling.(feature) 4) deny access to user if he/she has not scheduled the meeting.(Fixed) 5) Need to show the user details who scheduled the meeting.(Fixed) 6) While showing the error , please mention user selected time instead of current time.(removed current time) 7) All room booking showing that meeting is recurring, this need to be resolved.(fixed) | "Seat Booking: 1)The Layout uploaded is pixlated. 2)After Booking the seat the layout didnt highlited the booked seat. 3)The error MSG doesnt show what the error is. attaching the error on the screen shot screen. 4) The calender Tab doesnt show the seat and the Parking booking. 5)On parking booking cant see which slots are been booked
10 | Room Booking | 1 |  | Change |  | Invites should not edit Room booked by other user | invites can also edit | Fixed | YES
11 | desk booking | 1 |  | change |  | should get a proper error message when a user try to book two seats at a time | getting an error like "sorry undefined!" and in the background its showing an error like employee already booked a seat | FIxed | YES
17 | Room Booking | 1 |  | bug |  | Booking issue handle with round of minutes | Booking won't work on minutes rather then round of minutes i.e 9:02AM to 10:04AM = false and 9:05AM to 10:05AM = true | fixed | YES |  |  | fix with round minutes
18 | parking slot | 1 |  | bug |  | shoudnt get booked if we select the passed or finished dates | not getting any error if i book the slot on passed dates | Fixed and handled | YES
20 | Time selecting issue | 1 |  | change |  | end time should be greater than start time, before going to select a seat/parking slot. | end time should be greater than start time, at load. | fixed this issue on every from date change event Todate also changes to next 30 mins | YES
24 | desk booking | 1 |  | change |  | should have difference between booked and non-booked seats | there no differentiation between booked and non booked seats | Issue is fixed | YES
25 | parking slot | 1 |  | change |  | should have difference between booked and non-booked parking slots | there no differentiation between booked and non booked parking slots | Issue with Back-End API so please share this info to Venu | NO
26 | profile page | 1 |  | feature |  |  | update button is not visible in the profile page, so i couldnt enable thepush notifiation | Fixed | YES
29 | room booking | 1 |  | bug |  | shouldn't get booked without inviting members | but while editing meeting rooms, if i try to book room without inviting invitees, the room is getting booked | it won't happen with latest update so please check is you using latest coded app | YES |  |  |  | no its still there
35 | Sign in Page | 1 | iPhone XS | Bug | 10 |  | Always seem to get a message that User already logged in, even though I never used my credentails to log in to the web portal, although this was fixed after a call with Venu, but maybe its an issue with the app, Sindu can re-confirm | Sindhu cross check with Sign in and sign-out issue
36 | Booking Calendar Method | 1 | iPhone XS | Change | 11 |  | The way booking calendar selection is designed, needs to be better. We can have a drop down view, like it is for room selection | resolved
37 | Seat Selection | 1 | iPhone XS | Bug | 12 | Clicking on the seat once doesn't book the seat | Need to click on the seat multiple times to select it for booking, being so small on the screen, I am not even sure if the right seat was booked
38 | Booking Overview | 1 | iPhone XS | Bug | 14 |  | After confirming seat and desk booking, I could see no bookings on the main screen. Tried refreshing it 2-3 time with up and down pull, nothing happened I moved to seperate pages, profile, etc, even then I couldn't see my booking Tried booking another seat, booking couldn't be done as seat was already booked for that time, that is when I could see 2 bookings on overview page
41 | Calendar View | 1 | iPhone XS | Bug | 17 |  | Waited for 10 mins, Calendar view never loaded | If booking on that day then it won't show and i try to add message like "No History on this Day"
42 | Logout needs to be more prominent | 1 | iPhone XS | Change |  |  | The logout button needs to be more pronounced | Noted
46 | desk booking | 1 |  |  |  |  | cannot come out of the layout, without booking a seat and parking slot and cannot select any of the slots clicking 8 to 10times | Fixed |  |  |  | Doubled size of seat slot to click and sindhu test that issue Ipad
3 |  | 1 |  |  |  |  | while updating the time of booked events, its taking the wrong time and also displaying the wrong/negative duration | Fixed
9 |  | 1 |  |  |  |  | Not getting any error while editing if I try to book a seat or parking at same time which has already got booked
9 |  | 1 |  |  |  |  | Desk also taking wrong timings and giving negative duration after editing | Fixed
13 |  | 1 |  |  |  |  | The event is still running even after the time out | feature dev
27 |  | 1 |  |  |  |  | while updating the booked room, purpose not working correctly | Fixed
28 |  | 1 |  |  |  |  | we can select both asc and desc date | Fixed
7 |  | 1 |  |  |  |  | while editing room, it accepts the wrong or past time also | FIXED
3 | profile page | 2 |  | feature |  | should get push notification 10mins before the meeting starts and 10mins before the meeting ends | getting push notification 20mins before the meeting ends | Need to check API's of push notifications, Issue is fixed by Venu | YES |  |  |  | spelling errors - profile, supriya ; change mobile no to mobile number Show an indication that we can change profile photo Logout should be written with button to log out
4 | desk booking | 2 |  | feature | 2 | cannot exceed desk booking more than 24hrs duration | here its possible to book a desk for two contineous days | As of now we build in form of exsiting app 1.0 and we need to alter this after discussion and now it fixed | YES
7 |  | 2 |  | feature |  | should get an error if we miss to fill any options | we wont get any errors if we wouldn't select any options like date, time, amenities | next button will be gray out with out validation it won't turn to green | YES
9 |  | 2 |  | change |  | better to add the loader wherever required, otherwise it looks like mobile got hung |  | please mention us where loader required and you feel hang
13 | Clock UI mis fire | 2 |  | bug |  | clock UI fire when select Other properties and this only happens when clock cancels | Clock UI should be corrected | Noted
15 | room booking | 2 |  | feature |  | should give a notification like "room update successfully", once after editing the room | dint get any notifiction or pop-up message once after updating | Fixed | YES
38 | Room Booking Attendies | 2 | iPhone XS | Change | 13 |  | Cannot see the book logo without 'Informing Members' Lets keep attendies as an option, booking should allow me to add them in the meeting, and should also allow seperately to inform them with notification like we have on the web app | resolved
45 | room booking | 2 |  |  | 9 |  | while editing room booking, the days that we kept for repeat mode will get dissappear(refer the screenshot) | Issue is fixed
47 | room booking | 2 |  |  |  |  | no filters in the rooms once after selecting the rooms size | rsolved |  |  |  | it is fine any room size greater then select number is shown and i.e select 20 you dont get rooms
49 |  | 2 |  |  |  |  | couldn't book without inviting a members, need to change this feature like its there in the web app | resolved | yes |  |  | Fixed issue with only host need and invites is optional
50 |  | 2 |  |  |  |  | change the format while selecting time in the room booking, its not taking a proper time | resolved | yes |  |  | Issue with native Date and time picker and now we customized with another please review let us know
52 |  | 2 |  |  |  |  | manually we need to refresh the dashboard to see the scheduled events, make it automatic | Noted |  |  |  | This issue related to routing of pages if that issue fixed and parallely this issue also fix
11 |  | 2 |  |  |  |  | Time format of the schedules on the calender varies
14 |  | 2 |  |  |  |  | not giving any error msg on calender if no bookings found | Open Issue
6 |  | 2 |  |  |  |  | if meeting title left empty, gives error like "enter purpose" | Fixed
8 | desk booking | 3 |  | bug |  | should get an error if we book a seat which already got booked | not getting an error if we book a seat which already got booked | Fixed | YES
16 |  | 3 |  | feature |  | should get an error or shouldnt move forward if we dint select location, room or time an other attributes | not getting any error | Noted and fixed issue like step counter won't move by click on that | YES
31 | profile page | 3 |  |  |  |  | Not giving any error if i enter my personal id or any appropriate mail id
33 | desk and parking | 3 |  |  |  |  | while booking seat and parkng, the confirmation and the alert message contains different time format and also wrong duration | Fixed | YES
42 | Errors are displayed behind the popup | 3 | iPhone XS | Bug | 18 |  | Successful booking popup (Green) and unsuccessful booking popup (Yellow) and displayed behind the popup | Noted
48 | room booking | 3 |  |  |  |  | highlight the next button while selecting the room names, its quite confusing | resolved |  |  |  | Fixed issue with alert box
51 |  | 3 |  |  |  |  | no need to give the condition while entering the purpose of the meeting | Issue Fixed | yes |  |  | Removed all conditions related meeting Title
10 |  | 3 |  |  |  |  | Host is undefined on the calender
12 |  | 3 |  |  |  |  | Sometimes layout of parking slot not getting displayed and cannot come out of the layout then after and later session gets expired then again need to login | Fixed
15 |  | 3 |  |  |  |  | change from "purpose" to "meeting title" | Fixed
2 | dashboard | 4 |  | feature |  | booking schedules should display in the order, like ongoing meetings on the top,then the upcoming and later at the last the finished events |  | Need to implement |  |  |  |  | calendar loads very slowly Login page – Sign (In) is missing Calendar loading is very slow Cancel, Done, incomplete spelling Charts are blur
12 | Amenites should be wrap up | 4 |  | feature |  | add wrap view like users shown | now less amenties so looks fine but if amenties grow it should be take extra space | Feature
30 | room booking | 4 |  | feature |  | should be possible to edit all the options while editing | couldn't enter the purpose while editing the room | Fixed | YES
| 0 | [11 empty] | Supriya | Venugopal | Suraj Nair
5 | room booking |  |  | bug | 1 | once after filling all the reuqirements for room booking correctly, should get booked and get the confirmation mail | couldnt book a room once after filling all the requirements, getting an error like couldn't book, you have another meeting at this time though Ive tried with many differenting timings | solved | YES |  |  |  | not able to book room, after entering purpose, it's not allowing me to book
6 | dashboard |  |  | feature |  | should display the schedules on my dashboard, if i have been invited for any meeting by someone else | dashboard doesnt display any meeting schedules, if I got an invite | Solved | YES
14 | room booking |  |  | bug |  | room booked can be easily editable and should get the updated mail | couldnt edit the invitees, recurring days while editing the rooms | solved and added created user name | YES |  |  |  | 11 dec not yet resolved
19 | parking slot |  |  | feature |  | should get updated mail notification once after editing the booked slot | not getting updated email | Feature is not there in web app also so need implement and Venu should respond to this | NO
21 | room,desk,parking |  |  | change |  | after booking the seat or room, we will get a confirmation message at the last, it should display the booked date and time | its displaying the current time, little confusing | Removed current time displaying in confirmation View after booking | YES
22 | Room Booking |  |  | Bug |  |  | selecting and de-selecting room size is need not working | Fixed | YES
23 |  |  |  | change |  |  | no need of "recurring till " if its booked for single day | FIXED | YES
34 | desk booking |  |  |  |  | all seat names should look alike | some seat names are not appropriate
39 | Booking Time Selector |  | iPhone XS | Bug and Change | 15 |  | When choosing a booking date and time, It shows the calendar for entire month, and gives a small 'type in' method to add time in HH:MM format. After typing in the start time at 12:03, it confirmed that time Choosing the booking end time defaulted at 'Current system time' and when I wanted to book until 2 PM, the selector throws me out of the menu, and I have to start over again. The only successful booking that was possible was with default time selections for both room and desk. | i think u choose wrong version
40 | Floor Layout Resize |  | iPhone XS | Change | 16 |  | The floor layout seems very small, difficult to click on the right seat, should allow zooming in the layout How do I ensure which of these 3 seats I am clicking on on a 4.7 inch screen? (check screenshot) | Please give time to work on this feature
43 | room booking |  |  |  | 6 and 7 |  | while updating the booked room, the to-date is accepting passed or wrong date and also later getting updated | Noted
44 | room booking |  |  |  | 8 |  | couldnt enter the purpose, recurring date and also the invitees, refer the screenshot attached | Fixed
53 | [6 empty] | change the Amenities view, we can make it better as the web app | we can't alter like web app but we can configure amenities and select Room |  |  |  | we can't alter like web app but we can configure amenities and select Room
new issues
1 | [6 empty] | in the booking confirmation card, the time format differs | NO issue such like that
2 | [6 empty] | dashboard is not updating automatically | Fixed
4 | [6 empty] | no need of Asc and Desc order in the dashboard | Describe new Format and need discussion
5 | [6 empty] | couldn't edit the date, only time clock getting selected though i try to click on date and calender icon | only Time selection is possible on new Bookings
6 | [6 empty] | getting the same error as "no rooms found, tryu again with different cnfiguration" tjhough ive tried with all the room sizes and also with diff time slots | no issues like that please cross check
7 | [5 empty] | the legends at the top of the dashboard should be freeze | the legends are movable | fixed
8 | parking slot | [5 empty] | the layout is not visible to select a slot | Fixed with loader
16 | [6 empty] | the time clock disappear soon before selecting the minute | Fixed
17 | [6 empty] | remove end-date from desk and parking | discuss
18 | [6 empty] | instead of no repeat/repeat, we can change it as does this meeting repeats? like yes/no | Fixed
19 | [6 empty] | add attendies, like in web app | Fixed
20 | [6 empty] | add reverse shift like while booking we can go back and change the time,fdate, and rom also
21 | [6 empty] | give next button instead of layout view button on parking and desk booking | Fixed
22 | [6 empty] | change "from-date" to "from-time" | Fixed
23 | [6 empty] | remove 60 from the clock-time | Open Issue
24 | [6 empty] | time format should change according to the user mobile configuration | Not possible and future dev i can suggest add this User-role config
25 | [6 empty] | no need of size and amenities, selection of the room should give those properties defaultly like in web app | We given for configure rooms according our old mobileApp functionality concept and now remove can broke functionality
26 | [6 empty] | once after selecting the room instead of location, highlight the room size and amenities | Fixed
29 | [6 empty] | push notification
issues(v8.2)
1 | [6 empty] | couldn,t select amenities | Noted
2
3 | [6 empty] | once after selecting the time, the clozk still displays on the screen | According discussion we removed date from bookings
4 | [6 empty] | not getting push notififcation | should inform venu maybe issue with api's
5 | [6 empty] | couldn't edit the room, getting an error like "you've another meeting at this time" irrespective of the time | after removing Created rooms then booking is allowed so we need discuss with venu about this
8
overflow on the screen
9
date format varies allover
On android:
1 |  |  | 1 |  |  |  | soon after selecting the location, we can select only one amenities at a time |  | no
2 | [6 empty] | while adding attendies to the meeting, make it as attendies everywhere Instead of invites |  | no
3 | [6 empty] | cannot edit amenities, while editing the booked room |  | no
4 |  |  | 1 |  |  |  | If i try to book two rooms at the same time, its just give a toast like you cannot book, try with different configuration and the page just keeps loading, wouldn't move further
5 | [6 empty] | dashboard doesnt displays the meeting for which the user got an invite |  | yes
6 | [6 empty] | not getting any push notifications before the event starts
7 | [6 empty] | no need of recurring till date for the non-recurring meetings(on dashboard) |  | yes
8 | [6 empty] | provide confirmation alert box for parking slot also, as given for seat booking |  | yes
flors,layout view,settings page
29/12/2020
1 | login page | [5 empty] | confirm password should be encripted | No that is right format
2 | login page | [5 empty] | once after changing the password, if i give forgot password again, then again getting the same page i.e, the page is not getting refreshed | Fixed
3 | desk,room,parking | [5 empty] | not yet removed 60 from the time clock | Open Issue
4 | room booking | [5 empty] | coudn't edit amenities in room booking |  | no
5 | room booking | [5 empty] | though I selected and given the recurring date, its displaying the same from and to date on the dashboard
6 | room boking | [5 empty] | the list of invitees doesnt display all the members, while editing the room |  | yes
7 | room booking | [5 empty] | very rarely getting the updated mail for the booked room,
8
9 | room booking | [5 empty] | couldn't select multiple amenities while booking room |  | no
10 | desk, parking | [5 empty] | dint give any error message or toast if i try to book the seat or paking at the same time which already got booked, while editing |  | no
11 | room,paking,desk | [5 empty] | its getting booked if i enter the same start-time and to-time |  | no
12 | room,desk,parking | [5 empty] | the time clock gets disappear once after selecting the hours, again need to click on time slot to choose the minute hand |  | no
13 | login page | [5 empty] | google login-in is not working |  | no
14 | room booking | [5 empty] | doesnt display all the invitees, while editing the booked room
15 | dashboard | [5 empty] | dashboard doesnt dislpay the meetings for which user got an invite |  | yes
16 | room booking | [5 empty] | reverse shift is not working,like once after getting an error like "you've another meeting at this time" I cannot edit there itself, it will directly go to the home-page |  | yes
17 | [5 empty] | end-time shouldn't exceed that particular day i.e it shouldn't accept the next 24hrs | here the end-date is accepting the next day timings |  | no
18 | [5 empty] | the hour hand should be in 0 to 23hrs format | here its displaying from 0 to 24hrs format |  | no
19 | [5 empty] | the minute hand should be in 00 to 59mins format | here its displaying from 00 to 60mins format |  | no
20 | [6 empty] | sometimes fails to book a room, both on web and mobile app |  | no
21 | [6 empty] | not getting push notification for the invited meetings |  | no
22 | [6 empty] | the finished events are still displaying on the dashboard(Only on ipad)
23 | [6 empty] | google login not working |  | no
24 | [6 empty] | while editing the booked events, couldn't change the end-time alone |  | no
25 | [6 empty] | no need of "book a room" on the booking confirmation card |  | no
26 | [6 empty] | not getting mail notifications for room booking
27 | [6 empty] | change the time picker of seat and parking slot same as layout view

## screenshots
1
| Suraj nair | Gagandeep
10
2
11
3
12
5
13
6
14
7
8
15
9
16
17
18

## Interface Text Changes
I have made a PPT for interface text changes, here's the link.
https://docs.google.com/presentation/d/1gDHd_cLII5m22UJyFoBc6irDEcpumdcIUfulnI7Z3d0/edit?usp=sharing

## Error Messaging Changes
Sr No | Context | Existing Message | Suggested Message | Comments
1 |  | Sorry, we didn\'t store your data ! | Sorry, the data couldn't be stored
2 |  | Sorry, we need camera roll permissions to make this work | Please enable permissions to the camera roll
3 |  | Photo uploaded successfully | Image uploaded successfully
4 |  | Unable to upload the image | Couldn't upload the image, please try again
5 |  | response.msg |  | Please provide context to this error for right wordings
6 |  | Failed to add Push notification | Couldn't enable notifications, please try again
7 |  | response.msg |  | Please provide context to this error for right wordings
8 |  | error |  | Please provide context to this error for right wordings
9 |  | Must use physical device for SMS & Push Notifications |  | What do you mean by physical device here?, please provide context | this msg only comes when app in simulator
10 |  | Email is Empty | Email cannot be blank
11 |  | Email is not Valid | Invalid email, please try again
12 |  | Mobile no is Empty | Mobile no cannot be blank
13 |  | Mobile no is not Valid | Invalid number, please try again
14 |  | Must use physical device for SMS & Push Notifications |  | What do you mean by physical device here?, please provide context | this msg only comes when app in simulator
15 |  | Failed to get push token for push notification | Maybe - "Please enable notifications for this app in Settings" | User wouldn't know what a token is, please provide exact context for use of right words
16 |  | response.msg |  | Please provide context to this error for right wordings
17 |  | Failed to add Push notification | Couldn't enable notifications | Exact context will be helpful
18 |  | error |  | Please provide context to this error for right wordings
19 |  | data.msg |  | Please provide context to this error for right wordings
20 |  | this.state.empId+ |  | Please provide context to this error for right wordings
21 |  | data.msg |  | Please provide context to this error for right wordings
22 |  | this.state.empId+ |  | Please provide context to this error for right wordings
23 |  | You didn't selected slot |  | Do you mean time slot, or date slot here, please provide context
24 |  | You didn't selected slot |  | Do you mean time slot, or date slot here, please provide context
25 |  | Email is not valid or Empty | Blank or invalid Email id, please try again
26 |  | Password is Empty | Password cannot be empty, please try again
27 |  | Username is Empty | Username cannot be empty, please try again
28 |  | It is Saved Successfully | Saved successfully
29 |  | There was an error saving the product |  | Please provide context to this error for right wordings
30 |  | api _fetch err |  | If this is not user facing, it can stay the same | If internet is not connected to mobileApp
31 |  | Login with Token Successfully | Successfully logged in
32 |  | Token is Expired | Expired token
33 |  | Login with Token Successfully | Successfully logged in
34 |  | Session expired login again | Session expired, please login again
35 |  | Login with Token Successfully | Successfully logged in
36 |  | Session expired login again | Session expired, please login again
37 |  | Login with Token Successfully | Successfully logged in
38 |  | Login with Token Successfully | Successfully logged in
39 |  | Session expired login again | Session expired, please login again
40 |  | Session expired login again | Session expired, please login again
41 |  | Text length is too long |  | No change
42 |  | res.msg |  | Please provide context to this error for right wordings
43 |  | res.msg |  | Please provide context to this error for right wordings
44 |  | api _fetch err |  | If this is not user facing, it can stay the same
45 |  | Invalid Credentials |  | No change
46 |  | Please enter the password |  | No change
47 |  | Invalid email address | Invalid email, please try again
48 |  | Please enter the password |  | No change
49 |  | Username is less than 4 characters | Username cannot be less than 4 characters
50 |  | number must be ten digits | Number cannot be less than 10 digits
51 |  | Please enter OTP |  | No change
52 |  | Login Successful | Successfully logged in
53 |  | Login Error | Couldn't login, please try again
54 |  | res.msg |  | Please provide context to this error for right wordings
55 |  | Login Successful | Successfully logged in
56 |  | Error while Logging in | Couldn't log in, please try again
57 |  | res.err |  | Please provide context to this error for right wordings
58 |  | Login Successful | Successfully logged in
59 |  | Error while Logging in | Couldn't log in, please try again
60 |  | res.err |  | Please provide context to this error for right wordings
61 |  | Login Successful | Successfully logged in
62 |  | Login Error | Couldn't log in, please try again
63 |  | Login Error | Couldn't log in, please try again
64 |  | Login Successful | Successfully logged in
65 |  | Login Error | Couldn't log in, please try again
66 |  | Invalid Credentials |  | No change
67 |  | Invalid email address | Blank or invalid Email id, please try again
68 |  | Username is less than 4 caracters | Username cannot be less than 4 characters
69 |  | Domain not found, contact Admin | Cannot find the entered domain, please contact Admin to proceed
70 |  | Domain is Verifed | Domain verified
71 |  | res.msg |  | Please provide context to this error for right wordings
72 |  | res.msg |  | Please provide context to this error for right wordings
73 |  | res.msg |  | Please provide context to this error for right wordings
74 |  | res.msg |  | Please provide context to this error for right wordings
75 |  | OTP length should be 5 Digit | Please enter the 5 digit OTP
76 |  | res.msg |  | Please provide context to this error for right wordings
77 |  | res.msg |  | Please provide context to this error for right wordings
78 |  | OTP Field is Empty | Please enter the OTP
79 |  | New Password is invalid | New password invalid, please try again
80 |  | Confirm Password is invalid | Password confirmation invalid, please try again
81 |  | Password is not Matching | Both passwords do not match, please try again
82 |  | res.msg |  | Please provide context to this error for right wordings
83 |  | res.msg |  | Please provide context to this error for right wordings
84 |  | res.msg |  | Please provide context to this error for right wordings
85 |  | res.msg |  | Please provide context to this error for right wordings
86 |  | Fetching bookings... |  | No change
87 |  | api _fetch err |  | If this is not user facing, it can stay the same
88 |  | Session expired, login again | Session expired, please login again
89 |  | Can't edit as time up | Sorry, cannot edit an already passed event
90 |  | Invites can't edit this booking | Only the organizer can edit this booking
91 |  | DateTime should be more then Now | Please enter a future time
92 |  | DateTime should be more then Now | Please enter a future time
93 |  | Room booking has been deleted | Booking deleted successfully
94 |  | Something went Wrong |  | No change
95 |  | Booking has been deleted | Booking deleted successfully
96 |  | Something went Wrong
97 |  | Desk Schedule is Updated | Booking updated successfully
98 |  | Parking Schedule is Updated | Booking updated successfully
99 |  | data.msg |  | Please provide context to this error for right wordings
100 |  | Room are not selected | Please select a room
101 |  | resOfBooking.msg |  | Please provide context to this error for right wordings
102 |  | DateTime should be more then Now | Please enter a future time
103 |  | resOfBooking.msg |  | Please provide context to this error for right wordings

## To-do
| To-Do list |  | Developer comments
1 | Change the list view to “Bookings for Today”
2 | Social logins need to be created
3 | A permanent token is needed for the mobile app
4 | Layout view is required for room booking
5 | Filter for the city, building floor, selection of the room on floor layout needs to be implemented
6 | User location preferences need to be set in the profile view
7 | Back button needs to be added for booking, 1,2,3 top buttons can be clickable
8 | Follow “from time” and “to time” as per google calendar even for future dates
9 | Allow the user to have a different date selection, (today can be set as default)
10 | Once the date is selected, allow the user to choose “from time” and “to time”
11 | Implement time zone parameter for booking - check with Venu, how is it done for the web app
12 | Push notifications 2 times | *At the time of the booking the desk/room *10 mins before the booking time starts
13 | Enable SMS notifications
14 | Recommendations on text changes for notifications messages and email from Supriya
15 | Past events need to be removed from the “Today” page - fixed
16 | Have Calendar view, as well as Layout view for Room booking
17 | When choosing the room, it should not ask to select the room on ‘repeat booking’ page again
18 | Meeting title and attendees can be added on the calendar and time selection page only to keep the experience more efficient and simple
19 | Meeting conflicts needs to be highlighted before confirming the booking
20 | Keep screen 3 as a summary page of booking to confirm and book